## 20022017 Backlog
Priority | Product Backlog Item | Acceptance Criteria | Developer | Expected | Actual | Completion | Notes
| As an Administrator, I want to have a system that supports the information and data the system stores and uses. | It is possible to interact with and use data related to Teacher, Student, Course, and Class. | Oscar | 2 Hours | 2 Hours | 100% | Due to this being the base of the entire system, the database will be constantly altered and changed to accomidate any new information or data that the system is needed to support. At the base stage, it will merely support teachers, students, courses, and classes. These 4 are the core pieces of data the system needs to support.
| As an Administrator, I want to be able to Save the Information of the System. | Data and Information of the system is correctly saved to some external format. | Oscar | 2 Hours | 2 Hours | 100% | These 3 items are all associated with the aspect of saving and loading data into and out of the System. This was broken down into these 3 componenets, saving, loading, and translating, to divide it up into a more managable size. However, as these 3 items are all tightly connected, all 3 are worked on together and at the same time. Working on them seperately and combining them together would be proplematic.
| As an Administrator, i want to be able to Load the information of the System. | Data and Information from an external format is loaded into the system. | Oscar | 2 Hours | 2 Hours | 100%
| As a Developer, I want to be able to translate data back and forth between internal and external. | The system can correctly read data from either end and convert it into the proper format on the other side. | Oscar | 2 Hours | 2 Hours | 100%
| As a team, we all need to understand how to effectively work with the database and use it appropriately. [RESEARCH] | A breakdown of the databases components and example usage of various components to allow understanding of the system. Done as a Presentation of sorts | Oscar | 3 Hours
| As a Team, we need an understanding of TkInter in order to developer an approriate Graphical Interface for the system. [RESEARCH] | Multiple examples or instances of how TkInter is used are provided for the whole team to view and inspect with an explanation as how they work. | Matt | 8 Hours |  |  | These 2 items are top priority but are delayed due to not being able to utilize effectively without an already existing system working beforehand. These 2 items are also conjoined. The research portion should come before the actual implementation.
| As a User, I want to be able to view the system with an appropriate Graphical Interface. | The system can be viewed and used with a User Interface that allows easy access to the systems various functions.
| As an Administrator, I want to be able to add a Teacher to the school. | An administrator can correctly add a new Teacher to the system. | Ahsan | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to remove a Teacher from the school | An administrator can correctly remove a Teacher from the system. | Ahsan | 4 Hours | N/A | 70%
| As an Administrator, I want to be able to add a Course to the school. | An administrator can correctly add a new Course to the system. | Matt | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to remove a Course from the school. | An administrator can correctly remove a Course from the system.
| As an Administrator, I want to be able to add Students to the school. | An administrator can correctly add a Student to the system. | Lewie | 4 Hours | 4 Hours
| As an Administrator, I want to be able to remove a Student from the school. | An administrator can correctly remove a Student from the system. | Lewie | 4 Hours | 4 Hours
| As an Administrator, I want to be able to add a Class to the school. | An administrator can correctly add a Class to the system.
| As an Administrator, I want to be able to remove a Class from the school. | an Administrator can correctly remove a Class from the system.
| As a user, I want to be able to get a list of all Students in the school. | A user can view all Students currently attending school. | Lewie | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to find a specific Student's information. | A user can identify the Students name and any other relevant data. | Lewie | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to get a list of all Teachers in the school. | A user can view all Teachers currently working at the school. | Mo | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to find a specific Teacher's information. | A user can identify the Teachers name and any other relevant data. | Mo | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to get a list of all Courses in the school. | A user can view all Courses currently taught at the school.
| As a user, I want to be able to find a specific Course's information. | A user can identify the Course name and other relevant data. | Matt | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to get a list of all Classes in the school. | A user can view all Classes currenty taught at the school.
| As a user, I want to be able to find a specific Classes information. | A user can identify the Class name and all relevant data.
| As a teacher, I want to be able to put students in a Course. | A teacher can add students to a Courses saved data. | Oscar | 1 Hour
| As a teacher, I want to be able to remove a student from a Course. | A teacher can remove a student from a Courses data. | Oscar | 1 Hour
| As an Administrator, I want to be able to set a teacher to a Course. | An Administrator can set the teacher for a specific Course
| As an Administrator, I want to be able to remove a teacher from a Course. | An Administrator can remove a teacher from a specific Course.
| As a teacher, I want to be able to add a Class to a Course. | A teacher can add a Class to a Courses data.
| As a teacher, I want to be able to remove a Class from a course. | A teacher can remove a Class from a Courses data.
| As a user, I want to be able to view all Students in a Course. | A user can view all Students within a specific Course.
| As a user, I want to be able to view all Teachers in a Course. | A user can view all Teachers within a specific Course.
| As a user, I want to be able to view all Classes in a Course. | A user can view all Classes within a specific Course.
| As a teacher, I want to be able to put students in a Class. | A teacher can add students to a Classes saved data. |  |  |  |  | These items are all associated to Classes specifically and are low priority due to them relying on higher priority items that have yet to be done. These items will be focused on more when a larger amount of higher priority items are completed such as the items associated to Courses.
| As a teacher, I want to be able to remove students from a Class. | A teacher can remove students from a Classes data.
| As an Administrator, I want to be able to assign a teacher to a Class. | An Administrator can set a teacher for a specific Class.
| As an Administrator, I want to be able to remove a teacher from a Class. | An Administrator can remove a teacher from a specific Class.
| As a user, I want to be able to view all students in a Class. | A user can view all students within a specific Class.
| The system should support grades in some form or another. | Specifications Later. |  |  |  |  | The specifics of these tasks have yet to be looked into and will be discussed and planned out at later meetings when available.
| The system should support some form of attendence of Students. | Specifications Later.
| The system should support Student year. | Specifications Later.

## 06032017 Backlog
Priority | Product Backlog Item | Acceptance Criteria | Developer | Expected | Actual | Completion | Notes
| As an Administrator, I want to have a system that supports the information and data the system stores and uses. | It is possible to interact with and use data related to Teacher, Student, Course, and Class. | Oscar | 2 Hours | 2 Hours | 100%
| As an Administrator, I want to be able to Save the Information of the System. | Data and Information of the system is correctly saved to some external format. | Oscar | 2 Hours | 2 Hours | 100%
| As an Administrator, i want to be able to Load the information of the System. | Data and Information from an external format is loaded into the system. | Oscar | 2 Hours | 2 Hours | 100%
| As a Developer, I want to be able to translate data back and forth between internal and external. | The system can correctly read data from either end and convert it into the proper format on the other side. | Oscar | 2 Hours | 2 Hours | 100%
| As a team, we all need to understand how to effectively work with the database and use it appropriately. [RESEARCH] | A breakdown of the databases components and example usage of various components to allow understanding of the system. Done as a Presentation of sorts | Oscar | 3 Hours | 5 Hours | 100%
| As a Team, we need an understanding of TkInter in order to developer an approriate Graphical Interface for the system. [RESEARCH] | Multiple examples or instances of how TkInter is used are provided for the whole team to view and inspect with an explanation as how they work. | Matt and Mo | 8 Hours | 8 Hours | 50%
| As a User, I want to be able to view the system with an appropriate Graphical Interface. | The system can be viewed and used with a User Interface that allows easy access to the systems various functions. | Matt and Mo | 20 Hours
| As an Administrator, I want to be able to add a Teacher to the school. | An administrator can correctly add a new Teacher to the system. | Ahsan | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to remove a Teacher from the school | An administrator can correctly remove a Teacher from the system. | Ahsan | 4 Hours | 5 Hours | 100%
| As an Administrator, I want to be able to add a Course to the school. | An administrator can correctly add a new Course to the system. | Matt | 4 Hours | 5 Hours | 100%
| As an Administrator, I want to be able to remove a Course from the school. | An administrator can correctly remove a Course from the system. | Oscar | 1 Hour | 1 Hour | 100%
| As an Administrator, I want to be able to add Students to the school. | An administrator can correctly add a Student to the system. | Lewie | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to remove a Student from the school. | An administrator can correctly remove a Student from the system. | Lewie | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to add a Class to the school. | An administrator can correctly add a Class to the system. | Ahsan | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to remove a Class from the school. | an Administrator can correctly remove a Class from the system. | Ahsan | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to get a list of all Students in the school. | A user can view all Students currently attending school. | Lewie | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to find a specific Student's information. | A user can identify the Students name and any other relevant data. | Lewie | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to get a list of all Teachers in the school. | A user can view all Teachers currently working at the school. | Mo | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to find a specific Teacher's information. | A user can identify the Teachers name and any other relevant data. | Mo | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to get a list of all Courses in the school. | A user can view all Courses currently taught at the school. | Ahsan | 4 Hours
| As a user, I want to be able to find a specific Course's information. | A user can identify the Course name and other relevant data. | Matt | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to get a list of all Classes in the school. | A user can view all Classes currenty taught at the school. | Lewie | 4 Hours
| As a user, I want to be able to find a specific Classes information. | A user can identify the Class name and all relevant data. | Lewie | 4 Hours
| As a teacher, I want to be able to put students in a Course. | A teacher can add students to a Courses saved data. | Oscar | 1 Hour | 1 Hour | 100%
| As a teacher, I want to be able to remove a student from a Course. | A teacher can remove a student from a Courses data. | Oscar | 1 Hour | 1 Hour | 100%
| As an Administrator, I want to be able to set a teacher to a Course. | An Administrator can set the teacher for a specific Course | Mo | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to remove a teacher from a Course. | An Administrator can remove a teacher from a specific Course. | Mo | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to view all Students in a Course. | A user can view all Students within a specific Course. | Lewie | 3 Hours | 3 Hours | 100%
| As a user, I want to be able to view all Teachers in a Course. | A user can view all Teachers within a specific Course. | Lewie | 3 Hours | 3 Hours | 100%
| As a user, I want to be able to view all Classes in a Course. | A user can view all Classes within a specific Course. | Lewie | 3 Hours | 3 Hours | 100%
| As a teacher, I want to be able to set the course of a Class. | A teacher can set the course a class is listed under. | Oscar | 6 Hours | 1 Hour | 100%
| As a teacher, I want to be able to remove the course from a Class | A teacher can remove the course a class is listed under. |  |  | 1 Hour | 100%
| As a teacher, I want to be able to put students in a Class. | A teacher can add students to a Classes saved data. |  |  | 1 Hour | 100%
| As a teacher, I want to be able to remove students from a Class. | A teacher can remove students from a Classes data. |  |  | 1 Hour | 100%
| As an Administrator, I want to be able to assign a teacher to a Class. | An Administrator can set a teacher for a specific Class. |  |  | 1 Hour | 100%
| As an Administrator, I want to be able to remove a teacher from a Class. | An Administrator can remove a teacher from a specific Class. |  |  | 1 Hour | 100%
| As a user, I want to be able to view all students in a Class. | A user can view all students within a specific Class. |  |  | 1 Hour | 100%
| As a teacher, I want to be able to give students grades for a course. | A teacher can create a grade for a student with a course, student, and grade value.
| As a student, I want to be able to view all grades I have been given. | A student can view a list of all grades under their name.
| As a teacher, I want to be able to view all grades for a specific course. | A teacher can view a list of all grades under a specific course.
| As an Administrator, I want to be able to view all grades in the system. | An Administrator can view a list of all grades within the system.
| As an Administrator, I want students to be divided up by year. | The system can seperate students and similar by some form of year metric.
| As a student, I want to be able to see what year I am in. | A student can see the year they are in.
| As a teacher, I want to be able to view students by their year. | A teacher can see all students in a given year.
| As an Administrator, I want to be able to give a student a warning/offence if they misbehave. | An Administrator can increase the number of warnings a student has on their record.
| As an Administrator, I want to be able to see all warnings/offences that have been dealt. | An Administrator can view a list of all warnings in the system.
| As an Administrator, I want to be able to add a Club to the system. | An Administrator can add a new Club to the system.
| As an Administrator, I want to be able to remove a Club from the system. | An Administrator can remove an existing Club from the system.
| As a user, I want to be able to view all Clubs in the system. | A user can view a list of all clubs within the system.
| As a teacher, I want to be able to add students to a Club. | A teacher can add students to a specific clubs list.
| As a teacher, I want to be able to remove students from a Club. | A teacher can remove students from a specific clubs list.
| The system should support some form of attendence of Students. | To be Broken Down into components. |  |  |  |  | Further team discussion needed to better break it down into smaller tasks.
| User Accounts and Permissions | Admin, Teacher, Student, etc.
| Permission based UI | Access based on user permissions.
| Class Scheduling | Times when a class runs.
| System Improvements and Efficiency | Improving existing code and functionality

## 20032017 Backlog
Priority | Product Backlog Item | Acceptance Criteria | Developer | Expected | Actual | Completion | Notes
| As an Administrator, I want to have a system that supports the information and data the system stores and uses. | It is possible to interact with and use data related to Teacher, Student, Course, and Class. | Oscar | 2 Hours | 2 Hours | 100%
| As an Administrator, I want to be able to Save the Information of the System. | Data and Information of the system is correctly saved to some external format. | Oscar | 2 Hours | 2 Hours | 100%
| As an Administrator, i want to be able to Load the information of the System. | Data and Information from an external format is loaded into the system. | Oscar | 2 Hours | 2 Hours | 100%
| As a Developer, I want to be able to translate data back and forth between internal and external. | The system can correctly read data from either end and convert it into the proper format on the other side. | Oscar | 2 Hours | 2 Hours | 100%
| As a team, we all need to understand how to effectively work with the database and use it appropriately. [RESEARCH] | A breakdown of the databases components and example usage of various components to allow understanding of the system. Done as a Presentation of sorts | Oscar | 3 Hours | 5 Hours | 100%
| As a Team, we need an understanding of TkInter in order to developer an approriate Graphical Interface for the system. [RESEARCH] | Multiple examples or instances of how TkInter is used are provided for the whole team to view and inspect with an explanation as how they work. | Matt and Mo | 16 Hours | 16 Hours | 100%
| As a User, I want to be able to view the system with an appropriate Graphical Interface. | The system can be viewed and used with a User Interface that allows easy access to the systems various functions. | Matt and Mo | 80 Hours | (20 Hours) | 25% | Time estimated extended greatly based on the progress checks and other delays.
| As an Administrator, I want to be able to add a Teacher to the school. | An administrator can correctly add a new Teacher to the system. | Ahsan | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to remove a Teacher from the school | An administrator can correctly remove a Teacher from the system. | Ahsan | 4 Hours | 5 Hours | 100%
| As an Administrator, I want to be able to add a Course to the school. | An administrator can correctly add a new Course to the system. | Matt | 4 Hours | 5 Hours | 100%
| As an Administrator, I want to be able to remove a Course from the school. | An administrator can correctly remove a Course from the system. | Oscar | 1 Hour | 1 Hour | 100%
| As an Administrator, I want to be able to add Students to the school. | An administrator can correctly add a Student to the system. | Lewie | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to remove a Student from the school. | An administrator can correctly remove a Student from the system. | Lewie | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to add a Class to the school. | An administrator can correctly add a Class to the system. | Ahsan | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to remove a Class from the school. | An Administrator can correctly remove a Class from the system. | Ahsan | 4 Hours | 4 Hours | 100%
| As a developer, I want to be able to sort the data alphabetically. | The system can sort the data into an alphabetical order. | Lewie | 10 Hours
| As a developer, I want user accounts and permissions based access to the system. | The system should be able to tell who logs in and show different windows based on their permissions. | Matt, Mo and Oscar | 6 Hours
| As a user, I want to be able to get a list of all Students in the school. | A user can view all Students currently attending school. | Lewie | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to find a specific Student's information. | A user can identify the Students name and any other relevant data. | Lewie | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to get a list of all Teachers in the school. | A user can view all Teachers currently working at the school. | Mo | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to find a specific Teacher's information. | A user can identify the Teachers name and any other relevant data. | Mo | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to get a list of all Courses in the school. | A user can view all Courses currently taught at the school. | Ahsan | 4 Hours | 0.5 Hours | 100% | Task failed to be done during sprint. Taken over by Oscar
| As a user, I want to be able to find a specific Course's information. | A user can identify the Course name and other relevant data. | Matt | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to get a list of all Classes in the school. | A user can view all Classes currenty taught at the school. | Lewie | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to find a specific Classes information. | A user can identify the Class name and all relevant data. | Lewie | 4 Hours | 4 Hours | 100%
| As a teacher, I want to be able to put students in a Course. | A teacher can add students to a Courses saved data. | Oscar | 1 Hour | 1 Hour | 100%
| As a teacher, I want to be able to remove a student from a Course. | A teacher can remove a student from a Courses data. | Oscar | 1 Hour | 1 Hour | 100%
| As an Administrator, I want to be able to set a teacher to a Course. | An Administrator can set the teacher for a specific Course | Mo | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to remove a teacher from a Course. | An Administrator can remove a teacher from a specific Course. | Mo | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to view all Students in a Course. | A user can view all Students within a specific Course. | Lewie | 3 Hours | 3 Hours | 100%
| As a user, I want to be able to view all Teachers in a Course. | A user can view all Teachers within a specific Course. | Lewie | 3 Hours | 3 Hours | 100%
| As a user, I want to be able to view all Classes in a Course. | A user can view all Classes within a specific Course. | Lewie | 3 Hours | 3 Hours | 100%
| As a teacher, I want to be able to set the time and day a class takes place during the week. | A teacher can set the time and the day of a week a class takes place. |  | 3 Hours
| As a teacher, I want to be able to change the time and day a class takes place during the week. | A teacher can change the time and day of a week a class takes place. |  | 3 Hours
| As a teacher, I want to be able to give students grades for a course. | A teacher can create a grade for a student with a course, student, and grade value. | Oscar | 1 Hour
| As a student, I want to be able to view all grades I have been given. | A student can view a list of all grades under their name. | Oscar | 1 Hour
| As a teacher, I want to be able to view all grades for a specific course. | A teacher can view a list of all grades under a specific course. | Oscar | 1 Hour
| As an Administrator, I want to be able to view all grades in the system. | An Administrator can view a list of all grades within the system. | Oscar | 1 Hour
| As a teacher, I want to be able to set the course of a Class. | A teacher can set the course a class is listed under. | Oscar | 6 Hours | 1 Hour | 100%
| As a teacher, I want to be able to remove the course from a Class | A teacher can remove the course a class is listed under. |  |  | 1 Hour | 100%
| As a teacher, I want to be able to put students in a Class. | A teacher can add students to a Classes saved data. |  |  | 1 Hour | 100%
| As a teacher, I want to be able to remove students from a Class. | A teacher can remove students from a Classes data. |  |  | 1 Hour | 100%
| As an Administrator, I want to be able to assign a teacher to a Class. | An Administrator can set a teacher for a specific Class. |  |  | 1 Hour | 100%
| As an Administrator, I want to be able to remove a teacher from a Class. | An Administrator can remove a teacher from a specific Class. |  |  | 1 Hour | 100%
| As a user, I want to be able to view all students in a Class. | A user can view all students within a specific Class. |  |  | 1 Hour | 100%
| As an Administrator, I want students to be divided up by year. | The system can seperate students and similar by some form of year metric. |  | 4 Hours
| As a student, I want to be able to see what year I am in. | A student can see the year they are in. |  | 4 Hours
| As a teacher, I want to be able to view students by their year. | A teacher can see all students in a given year. |  | 4 Hours
| As an Administrator, I want to be able to give a student a warning/offence if they misbehave. | An Administrator can increase the number of warnings a student has on their record. |  | 4 Hours
| As an Administrator, I want to be able to see all warnings/offences that have been dealt. | An Administrator can view a list of all warnings in the system. |  | 4 Hours
| As an Administrator, I want to be able to add a Club to the system. | An Administrator can add a new Club to the system. |  |  |  |  | Not to be implemented
| As an Administrator, I want to be able to remove a Club from the system. | An Administrator can remove an existing Club from the system.
| As a user, I want to be able to view all Clubs in the system. | A user can view a list of all clubs within the system.
| As a teacher, I want to be able to add students to a Club. | A teacher can add students to a specific clubs list.
| As a teacher, I want to be able to remove students from a Club. | A teacher can remove students from a specific clubs list.
| The system should support some form of attendence of Students. | To be Broken Down into components. |  | N/A |  |  | Date Stored,Students attended,day by day basis
| As a developer, I want the system to run efficiently and properly. | All existing code should be checked and improved accordingly. |  | N/A

## 03042017 Backlog
Priority | Product Backlog Item | Acceptance Criteria | Developer | Expected | Actual | Completion | Notes
| As an Administrator, I want to have a system that supports the information and data the system stores and uses. | The system should support the priority types of data and information the system requires. Teacher, Student, Course, Class should all have some way of being stored and accessed within the system. | Oscar | 2 Hours | 2 Hours | 100%
| As an Administrator, I want to be able to Save the Information of the System. | The data and information of the system can be saved into a text format in order to be used at a later date | Oscar | 2 Hours | 2 Hours | 100%
| As an Administrator, i want to be able to Load the information of the System. | The data and information can be loaded from a text format saved beforehand for later use | Oscar | 2 Hours | 2 Hours | 100%
| As a Developer, I want to be able to translate data back and forth between internal and external. | The system can correctly convert text formatted data and information into the appropriate format within the systems code | Oscar | 2 Hours | 2 Hours | 100%
| As a team, we all need to understand how to effectively work with the database and use it appropriately. [RESEARCH] | A breakdown of the databases components and example usage of various components to allow understanding of the system. Done as a Presentation of sorts | Oscar | 3 Hours | 5 Hours | 100%
| As a Team, we need an understanding of TkInter in order to developer an approriate Graphical Interface for the system. [RESEARCH] | Multiple examples or instances of how TkInter is used are provided for the whole team to view and inspect with an explanation as how they work. | Matt and Mo | 16 Hours | 16 Hours | 100%
| As a User, i want to be able to view all functionality associated with Courses and use them. | The user is able to see a window that displays various widgets and similar which allow visual access to the functions associated with Courses. | Matt and Mo | 20 Hours | 15 Hours | 100%
| As a User, i want to be able to view all functionality associated with Classes and use them. | The user is able to see a window that displays various widgets and similar which allow visual access to the functions associated with Classes. | Matt, Mo
| As a User, i want to be able to view all functionality associated with Grades and use them. | The user is able to see a window that displays various widgets and similar which allow visual access to the functions associated with Grades. | Matt, Mo
| As a User, i want to be able to view all functionality associated with Students and use them. | The user is able to see a window that displays various widgets and similar which allow visual access to the functions associated with Students. | Matt, Mo | 10 Hours | 5 Hours | 100%
| As a User, i want to be able to view all functionality associated with Teachers and use them. | The user is able to see a window that displays various widgets and similar which allow visual access to the functions associated with Teachers. | Matt, Mo | 20 Hours | 20 Hours | 100%
| As a User, i want to be able to view all functionality associated with Attendence and use them. | The user is able to see a window that displays various widgets and similar which allow visual access to the functions associated with Attendence. |  | 25 Hours
| As a Teacher, i want to be able to login and access all functions specific to a Teacher. | A Teacher is able to see all functions a teacher can perform such as checking classes, giving grades, adding/removing students from a class, etc |  | 10 Hours
| As a Student, i want to be able to login and access all functions specific to a Student. | A Student is able to see all functions a student can perform such as checking what classes they take, what grades they have, who their teachers are. |  | 10 Hours
| As an Administrator, I want to be able to add a Teacher to the school. | A new teacher with the given Name will be added into the stored list of teachers within the system. | Ahsan | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to remove a Teacher from the school | A teacher existing in the stored list of teachers will be removed from that list. | Ahsan | 4 Hours | 5 Hours | 100%
| As an Administrator, I want to be able to add a Course to the school. | A new course will be added into the stored list of courses within the system. | Matt | 4 Hours | 5 Hours | 100%
| As an Administrator, I want to be able to remove a Course from the school. | A course existing in the stored list of courses will be removed from that list. | Oscar | 1 Hour | 1 Hour | 100%
| As an Administrator, I want to be able to add Students to the school. | A new student with a given Name will be added into the stored list of students within the system. | Lewie | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to remove a Student from the school. | A student existing in the stored list of students will be removed from that list. | Lewie | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to add a Class to the school. | A new class will be added into the stored list of clases within the system. | Ahsan | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to remove a Class from the school. | A class existing in the stored list of classes will be removed from that list. | Ahsan | 4 Hours | 4 Hours | 100%
| As a developer, I want to be able to sort the data alphabetically. | The data within the system can be organized into a basic alphabetical order. | Lewie | 12 Hours | 10 Hours | 50%
| As a developer, I want user accounts and permissions based access to the system. | The system (based on a login) should display different windows depending on who logged in. (Admin,Student,Teacher) | Matt, Mo and Oscar | 6 Hours | 4 Hours | 100%
| As a user, I want to be able to get a list of all Students in the school. | All students within the stored list are displayed. | Lewie | 4 Hours | 4 Hours | 100% | Method made redundant with the implementation of UI.
| As a user, I want to be able to find a specific Student's information. | A specific student within the stored list is displayed. | Lewie | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to get a list of all Teachers in the school. | All teachers within the stored list are displayed | Mo | 4 Hours | 4 Hours | 100% | Method made redundant with the implementation of UI.
| As a user, I want to be able to find a specific Teacher's information. | A specific teacher within the stored list is displayed. | Mo | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to get a list of all Courses in the school. | All courses within the stored list are displayed. | Ahsan | 4 Hours | 0.5 Hours | 100% | Task failed to be done during sprint. Taken over by Oscar Method made redundant with the implementation of UI.
| As a user, I want to be able to find a specific Course's information. | A specific course within the stored list is displayed. | Matt | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to get a list of all Classes in the school. | All classes within the stored list are displayed. | Lewie | 4 Hours | 4 Hours | 100% | Method made redundant with the implementation of UI.
| As a user, I want to be able to find a specific Classes information. | A specific class within the stored list is displayed | Lewie | 4 Hours | 4 Hours | 100%
| As a teacher, I want to be able to put students in a Course. | A existing student is added to the courses internal student list. | Oscar | 1 Hour | 1 Hour | 100%
| As a teacher, I want to be able to remove a student from a Course. | A existing student is removed from a courses internal student list. | Oscar | 1 Hour | 1 Hour | 100%
| As an Administrator, I want to be able to set a teacher to a Course. | The teacher of a course can be set to an existing teacher in the stored lists. | Mo | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to remove a teacher from a Course. | The teacher of a course can be removed to have no teacher. | Mo | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to view all Students in a Course. | All students in a courses internal student list are displayed. | Lewie | 3 Hours | 3 Hours | 100% | Method made redundant with the implementation of UI.
| As a user, I want to be able to view all Teachers in a Course. | All teachers associated with a course are displayed. | Lewie | 3 Hours | 3 Hours | 100% | Method made redundant with the implementation of UI.
| As a user, I want to be able to view all Classes in a Course. | All classes associated with a course are displayed. | Lewie | 3 Hours | 3 Hours | 100% | Method made redundant with the implementation of UI.
| As a teacher, I want to be able to set the time and day a class takes place during the week. | The time and day of week a class occurs can be set. | Oscar | 2 Hours | 0.5 Hours | 100%
| As a teacher, I want to be able to change the time and day a class takes place during the week. | A teacher can change the time and day of a week a class takes place. |  |  |  |  | Task is a duplicate of the above task.
| As a teacher, I want to be able to give students grades for a course. | A new grade is added to the stored lists with an associated course and student. | Oscar | 1 Hour | 0.25 Hours | 100%
| As a student, I want to be able to view all grades I have been given. | All grades under a given student are displayed. | Oscar | 1 Hour | 0.25 Hours | 100% | Method made redundant with the implementation of UI.
| As a teacher, I want to be able to view all grades for a specific course. | All grades under a given course are displayed. | Oscar | 1 Hour | 0.25 Hours | 100% | Method made redundant with the implementation of UI.
| As an Administrator, I want to be able to view all grades in the system. | All grades in the stored list are displayed. | Oscar | 1 Hour | 0.25 Hours | 100% | Method made redundant with the implementation of UI.
| As a teacher, I want to be able to set the course of a Class. | The course a class is associated with can be changed. | Oscar | 6 Hours | 1 Hour | 100%
| As a teacher, I want to be able to remove the course from a Class | The course a class is associated with can be remvoed to have no course. |  |  | 1 Hour | 100%
| As a teacher, I want to be able to put students in a Class. | A existing student is added to the classes internal student list. |  |  | 1 Hour | 100%
| As a teacher, I want to be able to remove students from a Class. | A existing student is removed from the classes internal student list. |  |  | 1 Hour | 100%
| As an Administrator, I want to be able to assign a teacher to a Class. | The teacher of a class can be set to an existing teacher in the stored lists. |  |  | 1 Hour | 100%
| As an Administrator, I want to be able to remove a teacher from a Class. | The teacher of a class can be removed to have no teacher. |  |  | 1 Hour | 100%
| As a user, I want to be able to view all students in a Class. | All students in a classes internal student list are displayed. |  |  | 1 Hour | 100% | Method made redundant with the implementation of UI.
| As a Teacher, I want to be able to take attendence of all student on a day. | The system should store a list of students with a status of A or T marking whether they attended or not. | Ahsan | 6 Hours
| As an Administrator, I want students to be divided up by year. | The system can seperate students and similar by some form of year metric. |  | 4 Hours |  |  | Discussion over implementation to be had.
| As a student, I want to be able to see what year I am in. | A student can see the year they are in. |  | 4 Hours
| As a teacher, I want to be able to view students by their year. | A teacher can see all students in a given year. |  | 4 Hours
| As an Administrator, I want to be able to give a student a warning/offence if they misbehave. | An Administrator can increase the number of warnings a student has on their record. |  | 4 Hours
| As an Administrator, I want to be able to see all warnings/offences that have been dealt. | An Administrator can view a list of all warnings in the system. |  | 4 Hours
| As an Administrator, I want to be able to add a Club to the system. | An Administrator can add a new Club to the system. |  |  |  |  | Not to be implemented
| As an Administrator, I want to be able to remove a Club from the system. | An Administrator can remove an existing Club from the system.
| As a user, I want to be able to view all Clubs in the system. | A user can view a list of all clubs within the system.
| As a teacher, I want to be able to add students to a Club. | A teacher can add students to a specific clubs list.
| As a teacher, I want to be able to remove students from a Club. | A teacher can remove students from a specific clubs list.
| As a developer, I want the system to run efficiently and properly. | All existing code should be checked and improved accordingly. |  | N/A