## 6-20 Feb 2017
6th February 2017 - 20th February 2017
Priority | Product Backlog Item | Acceptance Criteria | Developer | Expected | Actual | Completion | Notes
| As an Administrator, I want to have a system that supports the information and data the system stores and uses. | It is possible to interact with and use data related to Teacher, Student, Course, and Class. | Oscar | 2 Hours | 2 Hours | 100% | Due to this being the base of the entire system, the database will be constantly altered and changed to accomidate any new information or data that the system is needed to support. At the base stage, it will merely support teachers, students, courses, and classes. These 4 are the core pieces of data the system needs to support.
| As an Administrator, I want to be able to Save the Information of the System. | Data and Information of the system is correctly saved to some external format. | Oscar | 2 Hours | 2 Hours | 100% | These 3 items are all associated with the aspect of saving and loading data into and out of the System. This was broken down into these 3 componenets, saving, loading, and translating, to divide it up into a more managable size. However, as these 3 items are all tightly connected, all 3 are worked on together and at the same time. Working on them seperately and combining them together would be proplematic.
| As an Administrator, i want to be able to Load the information of the System. | Data and Information from an external format is loaded into the system. | Oscar | 2 Hours | 2 Hours | 100%
| As a Developer, I want to be able to translate data back and forth between internal and external | The system can correctly read data from either end and convert it into the proper format on the other side. | Oscar | 2 Hours | 2 Hours | 100%
| As an Administrator, I want to be able to add a Teacher to the school. | An administrator can correctly add a new Teacher to the system. | Ahsan | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to remove a Teacher from the school | An administrator can correctly remove a Teacher from the system. | Ahsan | 4 Hours | 4 Hours | 70%
| As an Administrator, I want to be able to add a Course to the school. | An administrator can correctly add a new Course to the system. | Matt | 4 Hours | 4 Hours | 80% | Task finished shortly after meeting with the help of another team member.
| As a user, I want to be able to get a list of all Students in the school. | A user can view all Students currently attending school. | Lewie | 4 Hours | 4 Hours | 100% | Due to being developed without a concrete database already existing, the current information displayed in relation to the repsective search may differ to what is shown at a later date when further implementation is done to combine these functions with the working database. As well as the database being subject to various changes as the system evolves
| As a user, I want to be able to get a list of all Teachers in the school. | A user can view all Teachers currently working at the school. | Mo | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to find a specific Teacher's information. | A user can identify the Teachers name and any other relevant data. | Mo | 4 Hours | 3 Hours | 100%
| As a user, I want to be able to find a specific Student's information. | A user can identify the Students name and any other relevant data. | Lewie | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to find a specific Course's information. | A user can identify the Course name and other relevant data. | Matt | 4 Hours | 4 Hours | 100%
|  |  |  | 40 Hours | 39 Hours

## 20-6 Feb-Mar 2017
20th February 2017 - 6th March 2017
Priority | Product Backlog Item | Acceptance Criteria | Developer | Expected | Actual | Completion | Notes
| As a Team, we need an understanding of TkInter in order to developer an approriate Graphical Interface for the system. [RESEARCH] | Multiple examples or instances of how TkInter is used are provided for the whole team to view and inspect with an explanation as how they work. | Matt and Mo | 8 Hours | 8 Hours | 100%
| As a team, we all need to understand how to effectively work with the database and use it appropriately. [RESEARCH] | A breakdown of the databases components and example usage of various components to allow understanding of the system. Done as a Presentation of sorts | Oscar | 3 Hours | 5 Hours | 100%
| As an Administrator, I want to be able to add Students to the school. | An administrator can correctly add a Student to the system. | Lewie | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to remove a Student from the school. | An administrator can correctly remove a Student from the system. | Lewie | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to remove a Teacher from the school | An administrator can correctly remove a Teacher from the system. | Ahsan | 1 Hour | 1 Hour | 100%
| As an Administrator, I want to be able to add a Course to the school. | An administrator can correctly add a new Course to the system. | Matt | 1 Hour | 1 Hour | 100%
| As an Administrator, I want to be able to add a Class to the school. | An administrator can correctly add a Class to the system. | Ahsan | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to remove a Class from the school. | an Administrator can correctly remove a Class from the system. | Ahsan | 4 Hours | 4 Hours | 100%
| As a teacher, I want to be able to put students in a Course. | A teacher can add students to a Courses saved data. | Oscar | 1 Hour | 1 Hour | 100%
| As a teacher, I want to be able to remove a student from a Course. | A teacher can remove a student from a Courses data. | Oscar | 1 Hour | 1 Hour | 100%
| As an Administrator, I want to be able to set a teacher to a Course. | An Administrator can set the teacher for a specific Course | Mo | 4 Hours | 4 Hours | 100%
| As an Administrator, I want to be able to remove a teacher from a Course. | An Administrator can remove a teacher from a specific Course. | Mo | 4 Hours | 4 Hours | 100%
|  |  |  | 39 Hours | 41 Hours

## 6-20 March 2017
6th March 2017 - 20th March 2017
Priority | Product Backlog Item | Acceptance Criteria | Developer | Expected | Actual | Completion | Notes
| As a User, I want to be able to view the system with an appropriate Graphical Interface. | The system can be viewed and used with a User Interface that allows easy access to the systems various functions. | Matt and Mo | 20 Hours | 20 Hours | 25% | Specifics: This sprint will focus on developing the UI to support the Teacher functions of the system.
| As a Team, we need an understanding of TkInter in order to developer an approriate Graphical Interface for the system. [RESEARCH] | Multiple examples or instances of how TkInter is used are provided for the whole team to view and inspect with an explanation as how they work. | Matt and Mo | 16 Hours (8 Hours) | 8 Hours (8 Hours) | 100%
| As an Administrator, I want to be able to remove a Course from the school. | An administrator can correctly remove a Course from the system. | Oscar | 1 Hour | 1 Hour | 100%
| As a user, I want to be able to get a list of all Courses in the school. | A user can view all Courses currently taught at the school. | Ahsan | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to get a list of all Classes in the school. | A user can view all Classes currenty taught at the school. | Lewie | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to find a specific Classes information. | A user can identify the Class name and all relevant data. | Lewie | 4 Hours | 4 Hours | 100%
| As a user, I want to be able to view all Students in a Course. | A user can view all Students within a specific Course. | Lewie | 3 Hours | 3 Hours | 100% | Assistance given by Oscar in order to code directly into the system instead of seperately
| As a user, I want to be able to view all Teachers in a Course. | A user can view all Teachers within a specific Course. | Lewie | 3 Hours | 3 Hours | 100%
| As a user, I want to be able to view all Classes in a Course. | A user can view all Classes within a specific Course. | Lewie | 3 Hours | 3 Hours | 100%
| As a teacher, I want to be able to set the course of a Class. | A teacher can set the course a class is listed under. | Oscar | 6 Hours | 1 Hour | 100%
| As a teacher, I want to be able to remove the course from a Class | A teacher can remove the course a class is listed under. |  |  | 1 Hour | 100%
| As a teacher, I want to be able to put students in a Class. | A teacher can add students to a Classes saved data. |  |  | 1 Hour | 100%
| As a teacher, I want to be able to remove students from a Class. | A teacher can remove students from a Classes data. |  |  | 1 Hour | 100%
| As an Administrator, I want to be able to assign a teacher to a Class. | An Administrator can set a teacher for a specific Class. |  |  | 1 Hour | 100%
| As an Administrator, I want to be able to remove a teacher from a Class. | An Administrator can remove a teacher from a specific Class. |  |  | 1 Hour | 100%
| As a user, I want to be able to view all students in a Class. | A user can view all students within a specific Class. |  |  | 1 Hour | 100%
|  |  |  | 56 Hours | 52 Hours

## 20-3 Mar-Apr 2017
6th March 2017 - 20th March 2017
Priority | Product Backlog Item | Acceptance Criteria | Developer | Expected | Actual | Completion | Notes
| As a User, I want to be able to view the system with an appropriate Graphical Interface. | The system can be viewed and used with a User Interface that allows easy access to the systems various functions. | Matt, Mo (Assisted by Oscar) | (80 hours total for task) 30 hours for this sprint | 20 Hours | 50% | Specifics: This sprint will focus on developing the UI to support the Student and Course functions of the system.
| As a developer, I want to be able to sort the data alphabetically. | The system can sort the data into an alphabetical order. | Lewie | 10 Hours | 10 Hours | 50% | Upon review, Code found to not do what is requried.
| As a developer, I want user accounts and permissions based access to the system. | The system should be able to tell who logs in and show different windows based on their permissions. | Matt, Mo and Oscar | 6 Hours | 4 Hours | 100% | These tasks will be done while working on the UI.
| As a teacher, I want to be able to give students grades for a course. | A teacher can create a grade for a student with a course, student, and grade value. | Oscar | 1 Hour | 0.25 Hours | 100%
| As a student, I want to be able to view all grades I have been given. | A student can view a list of all grades under their name. | Oscar | 1 Hour | 0.25 Hours | 100%
| As a teacher, I want to be able to view all grades for a specific course. | A teacher can view a list of all grades under a specific course. | Oscar | 1 Hour | 0.25 Hours | 100%
| As an Administrator, I want to be able to view all grades in the system. | An Administrator can view a list of all grades within the system. | Oscar | 1 Hour | 0.25 Hours | 100%
|  |  |  | 50 Hours | 35 Hours

## 3-24 April 2017
3rd April 2017 - 24th April 2017
Priority | Product Backlog Item | Acceptance Criteria | Developer | Expected | Actual | Completion | Weight | Notes
| As a User, i want to be able to view all functionality associated with Classes and use them. | The user is able to see a window that displays various widgets and similar which allow visual access to the functions associated with Classes. | Matt, Mo | 10 Hours | 8 Hours | 75% | 30%
| As a User, i want to be able to view all functionality associated with Grades and use them. | The user is able to see a window that displays various widgets and similar which allow visual access to the functions associated with Grades. | Matt, Mo | 20 Hours | N/A | N/A | 30%
| As a developer, I want to be able to sort the data alphabetically. | The data within the system can be organized into a basic alphabetical order. | Lewie | (15 hours total for task) 2 hours for this sprint | 2 Hours | 100% | 15% | Current algorithm needs to be changed to properly check and sort the items in the lists. This has been done
| As a teacher, I want to be able to set the time and day a class takes place during the week. | The time and day of week a class occurs can be set. | Oscar | 2 Hours | 0.5 Hours | 100% | 10%
| As a Teacher, I want to be able to take attendence of all student on a day. | The system should store a list of students with a status of A or T marking whether they attended or not. | Ahsan | 6 Hours | N/A | N/A | 15%
|  |  |  | 40 Hours | 10.5 Hours | 47.5%

## 24-X April 2017
24th April 2017 - X 2017
Priority | Product Backlog Item | Acceptance Criteria | Developer | Expected | Actual | Completion | Weight | Notes